## Slide 1: WP6 — AI Skills & Training
Vida Groznik · University of Ljubljana · WP6 Lead
SLAIF Mid-Term Review · Months 1–7 Progress

## Slide 2: Why WP6 matters for SLAIF
Infrastructure without skills is an empty computing centre.
WP6 builds the Slovenian AI & HPC talent pipeline — from doctoral students to SME decision-makers — that will put SLAIF's 100-petaflop supercomputer and its service portfolio to work across industry, academia and the public sector.

## Slide 3
WP6 at a glance
Lead: University of Ljubljana · Start M1 · End M36 · All 10 consortium partners active
4
Tasks
Talent · Customisation ·
SME engagement · Onboarding
338
Person-months
Total planned effort across
the 36-month project
10
Partners
Universities, research institutes,
chamber of commerce, tech park
3
Regional hubs
Ljubljana · Maribor · Novo mesto
+ extensions in Koper & Nova Gorica
Mission
Develop AI and HPC talent through customised training programmes that address the needs of diverse users — students, professionals, SMEs and public sector — foster SME engagement through accessible learning pathways, and establish onboarding activities that support new users in integrating AI into their workflows.

## Slide 4
The four-task architecture of WP6
Each task owned by a different institution — effort mirrors strategic weight
T6.1
AI Talent Development
Lead: UL FRI
Curricula · micro-credentials ·
MOOC · train-the-trainer · registry
T6.2
Customising Training
for Diverse Users
Lead: UM FERI
Needs analysis · 3-level pathway · sector-specific modules · MOOC content
T6.3
SME & Industry
Engagement
Lead: JSI
AI Industry Days · case studies ·
polls & feedback · SME-tailored training
T6.4
Onboarding Activities
for New Users
Lead: FIS
Regional hubs · helpdesk · orientation materials · site visits · consultancy
All 10 partners contribute to at least two tasks. Weekly WP6 coordination meetings have run since October 2025.

## Slide 5: Part II What we delivered in Months 1–7 Foundations, a training catalogue, a working infrastructure, and first industry contacts

## Slide 6
A consolidated training portfolio
First coordination output: one catalogue, one schema, one registry — published as Appendix C to the PPR
From 96 proposals
88
consolidated training activities
scheduled across the project lifecycle
Collected from all 10 partners between December 2025 and February 2026, deduplicated through iterative review
By training type
Workshops & hands-on sessions
59
Webinars for broader outreach
16
Micro-credential courses (EQF-aligned)
13
52 trainings combine lectures with practical exercises
34 delivered in Slovenian · 18 in English · 36 bilingual

## Slide 7
Thematic coverage across the full AI/HPC stack
Balanced portfolio — from fundamentals to frontier, with deliberate SME focus
Data science & ML fundamentals
19
HPC infrastructure & workflows
18
LLMs & natural language processing
16
AI adoption for SMEs & industry
12
Health & biomedical AI
11
AI ethics & EU AI Act compliance
6
Earth observation & agriculture
3
Computer vision
2
Cybersecurity
1
Nearly a third of the catalogue (33 of 88) targets SMEs, industry AI adoption and EU AI Act compliance — directly addressing the industry-facing mandate of the AI Factory.

## Slide 8
Training example
Adapting and fine-tuning LLMs – A hands-on approach for business and science
Course provider: University of Ljubljana, Faculty of Computer and Information Science (UL FRI) Instructors: Marko Robnik-Šikonja, Aleš Žagar, Matej Klemen, Domen Vreš, Tjaša Arčon, Živa Štebljaj
Learning Objectives
Get practical knowledge on how to use large language models (LLMs) via API calls, their fine-tuning for specific tasks, and efficient inference.
Course Content
To use large language models (LLMs) in a research or business setting, it is necessary to i) access them on local computers or on GPU servers via API, ii) adapt them to specific needs by fine-tuning them. The hands-on workshop will present theoretically and practically, step-by-step:
1. How LLMs can be used via API on a local or remote server.
2. How to fine-tune encoder-only models such as BERT.
3. How to fine-tune generative models such as Llama, Gemma, and GaMS using compute- efficient techniques such as LoRA.
4. How to implement efficient LLM inference.
The work will be based on practical datasets and problems from business and research environments. The use cases will cover popular tasks such as sentiment prediction, information retrieval, and question answering.
The independent work consists of an assignment using the dataset of your choice, preferably from your business or scientific domain (to be approved by the workshop team). The assignment shall fine-tune a suitable LLM on the prepared data, evaluate the results, and write a report, presenting the problem, methodology, evaluation, results, and conclusions.
Learning Outcomes
Practical knowledge of LLM API use and fine-tuning. Practical problem-solving skills with LLMs. Ability to independently solve problems with LLMs.
Prerequisites: /
Target audience
Advanced users of large language models
Language
English
Format
Hands-on sessions; Home assignments
Tentative date
Fall 2026, Spring 2027&28
Duration
Contact hours: 6h, Independent work: 54h
ECTS credits
2

## Slide 9
Training example
From exploratory data analysis to changing business processes using AI
Course provider: University of Ljubljana, Faculty of Computer and Information Science (UL FRI) Instructors: Slavko Žitnik, Timotej Knez, Miha Malenšek
Learning Objectives
Understand the transition from exploratory data analysis (EDA) to production-grade AI in business processes. Connect data-driven insights with decision-making and business process transformation. Use modern AI frameworks and large language models (LLMs) to support analysis, automation, and decision-making. Assess when and how AI can meaningfully transform existing workflows. Address organizational, technical, and ethical challenges of deploying AI in business environments.
Course Content
Candidates will get to know how to get from a research analysis to business insights (exploratory data analysis, hypothesis generation, visualization, interpretation), link data to business processes (identifying processes where AI adds value, measurable impact, KPIs), use LLMs for analysis and decision support (such as ChatGPT, Gemini, GaMS, and related LLMs for text analysis, summarization, decision support, and user interaction), use frameworks for building AI-powered solutions (such as LangChain and similar tools to connect models, data sources, tools, and business logic), how to come from a prototype to a process change (integration of AI solutions into existing IT systems, task automation, human-in-the-loop approaches, change management), and get to know risks, limitations, and responsible AI.
Learning Outcomes
By the end of the training, candidates will have learned to perform exploratory data analysis and link results to concrete business questions, identify business processes suitable for AI-enabled support or transformation, apply LLMs and AI frameworks to support analysis, decision-making, and automation, plan the transition from experimental AI solutions to changes in business processes, critically evaluate the impact of AI on organizations, employees, and business performance.
Prerequisites: /
Target audience
Team leads, chief information officers
Language
Slovenian, English
Format
Lectures; Hands-on sessions; Home assignments
Tentative date
Fall 2027, Summer 2028
Duration
Contact hours: 16h, Independent work: 32h
ECTS credits
2

## Slide 10
Training IT infrastructure — operational by M7
Two platforms, one registry — all discoverable, manageable and KPI-reportable
MOOC platform
edu.slaif.si
Central repository: lecture notes, source code, Jupyter notebooks, supplementary materials
Interactive teaching: integrated quizzes, assignments, homework submission, remote assessment
Dedicated GitHub organisation for source code management
Standardised content structure: landing pages, code blocks, callouts, example annotations
Consortium-wide onboarding target: May 2026
Indico event system
indico.slaif.si
Open-source event management, hosted at JSI, customised with SLAIF identity
Participant registration, event scheduling, automated notifications, attendance tracking
Synchronised with the SLAIF website, filterable by topic tags
Standardised templates: feedback survey, attendance certificate, sign-in sheet
Operational in testing since March 2026
Both platforms feed a single training registry that is the authoritative source for the training catalogue and KPI reporting.

## Slide 11
Micro-credentials — progress across the consortium
Governance framework in place; first formal accreditation achieved by Month 7
UNG
Accredited by Senate
Hands-on Machine Learning
First SLAIF micro-credential — formally accredited during M1–M7
FIS
Accreditation
applications filed
4 HPC intensive courses
Linux & containers · BERTopic · RAG · parallel GPU processing
UL
Courses developed
2 micro-credential courses
HPC infrastructure for AI workflows · Containers, CI/CD & Kubernetes
UM
Requirements analysed
Framework analysis
Participated in Design of Short Educational Programs workshop (March 2026)
UP
Templates compiled
Procedural documentation
Application forms, learning-plan templates, public certificate specimens
Governance framework
Shared repository for accreditation templates and institutional guidelines; all certifications aligned with the European Qualifications Framework, ensuring portability across consortium institutions.

## Slide 12
Reaching industry — first Open Day & SME channels
From listening to designing: survey responses already shaping the training roadmap
1st SLAIF Industry Open Day
17 November 2025 · JSI, Ljubljana
42
survey responses
in the WP6 session
Results compiled into dedicated presentation, shared with all 10 WP6 partners
Findings directly influenced selection of micro-credential topics
ARNES designed new workshop — Building a Data Culture — in direct response to the identified #1 barrier: data acquisition, curation & management
SME engagement channels
GZS — Chamber of Commerce & Industry of Slovenia
5,300+
member companies reachable through newsletters & direct outreach
3 business-tailored webinars designed:
Artificial Intelligence for Leadership
Early industrial contacts: Hidria · Steklarna Hrastnik · Domel · MESI · Caretronic
AI for Small Businesses
Artificial Intelligence in Entrepreneurship

## Slide 13
Regional hub network — physical presence across Slovenia
Low-threshold entry points for students, researchers, SMEs and public sector users
Ljubljana
UL FRI
Operational
SLAIF co-working space / office — showcases, informal consultations, partner collaboration
Ljubljana
TPLJ
Operational
Demo AI Factory Training Centre — opened February 2026; AI Hub since September 2025
Novo mesto
FIŠ
Operational
Dedicated training room · 10 pre-configured laptops · validated test accounts
Maribor
UM
In setup
Planned regional AI Factory training centre — onboarding protocols and user guides in design
Koper
UP
In setup
Co-working space under development — low-threshold entry for self-directed learners

## Slide 14
Training is already happening — not only planned
Signal deliveries during the reporting period validated our approach before the formal start
Oct 2025
HPC Open Doors Day
299 primary & secondary school students reached
(ARNES + JSI + UL, with SLING)
Nov 2025
1st SLAIF Industry
Open Day
42 WP6 survey responses
from industry representatives at JSI, Ljubljana
Jan-April 2026
ARNES HackathON
100 students gained
hands-on HPC experience
on ARNES Learning Cluster
Feb 2026
TPLJ Demo AI Factory
Training Centre opened
Physical training infrastructure for startup & SME cohorts in Ljubljana
Winter 25/26
FIŠ doctoral course
delivered
5 PhD students completed Transformer topic modelling · RAG
on HPC — reusable template

## Slide 15: Part III Where we go next Roadmap to M12 and KPI trajectory

## Slide 16
Roadmap: from preparation to delivery — M8 to M12
Milestone 2 target (M12): Core Services Operational — including commencement of initial training programmes
1
M8
April 2026
Consortium-wide
MOOC onboarding
All partners trained on edu.slaif.si; first MOOC content deposited
2
M8-M10
April-Jun 2026
Launch of FIŠ HPC
intensive courses
Linux & containers, BERTopic, RAG, GPU processing — first deliveries
3
M8
April 2026
Second AI Industry Day
Vertical-specific; SME demonstrations with WP5 services
4
M8-M12
April-August 2026
Micro-credential courses prepared for accreditation
Formal accreditation paperwork prepared and filed for courses delivered in 2026 and 2027
5
M12
Aug 2026
Deliverable D6.1
+ first-year catalogue
First-year progress report; micro-credentials open for enrolment
Phase transition
We are shifting from training-programme design to training-programme delivery. Infrastructure, governance and partner network are ready — the next seven months are about volume, feedback, and iteration.
Priority 1: HPC hands-on trainings; Priority 2: SME onboarding; Priority 3: micro-credential courses;

## Slide 17
KPIs driven by WP6
Six mandatory and eight non-mandatory KPIs — several already showing early contributions
KPI
Indicator
How WP6 drives it
M1–M7 status
5
AI training sessions provided
Driven by all 4 tasks; MOOC & train-the-trainer multiply reach
First trainings already started
10
AI-dedicated researchers in the AI Factory
T6.1 talent pipeline · T6.3 industry practitioners · T6.4 onboarded users
WP6 is the only WP growing it
11
Students participating in AI Factory activities
Already >400: 299 at HPC Open Doors + 100 at HackathON + 5 PhD course
Early traction
14
Micro-certifications introduced
Portfolio across UNG, FIS, UL, UM, UP — all EQF-aligned
First accreditation (UNG) done
15
New university courses on AI Factory topics
Driven by T6.1 and T6.2; UM gap analysis identifies priorities
In design
16
Registered HPC and AI certified specialists
Grows as learners complete micro-certifications and pass assessments
Starts M12
17
HPC and AI hackathons organised
HackathON delivered; annual cadence planned
1 delivered
18
AI Factory training centres established
Novo mesto · Ljubljana (2) operational; Maribor & Koper in setup
3 of 3 progressing
19
Cities toured with outreach & workshops
Ljubljana · Novo mesto · Maribor + further regional reach via GZS network
On track for 15 by project end
20
Application-area use case workshops
Aligned to WP5 verticals: green transition, health, digital society, science
Starting M8
21
AI Factory workshops at HPC events in Slovenia
SLING Days 2025 · ASHPC26 · embedded in national HPC calendar
Active

## Slide 18
Our message to the reviewers
WP6 has moved from a plan on paper to a running operation.
88 training activities catalogued · 2 platforms live · first micro-credential accredited ·
3 regional hubs operating or in setup · 400+ learners already touched · weekly cadence since October 2025

## Slide 19
Thank you for your attention!
© 2026 by SLAIF, licensed under CC BY-SA 4.0
SLAIF: Slovenska tovarna umetne inteligence je prejela financiranje Skupnega podjetja za evropsko visokozmogljivo računalništvo v okviru sporazuma o nepovratnih sredstvih št. 101254461. Projekt financirata Ministrstvo za visoko šolstvo, znanost in inovacije Republike Slovenije ter program Horizon Europe Evropske unije. SLAIF: Slovenian AI Factory has received funding by the European High Performance Computing Joint Undertaking under the grant agreement no. 101254461. The project is funded by the Ministry of Higher Education, Science and Innovation of Republic of Slovenia and by Horizon Europe Programme of the European Union.